## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Soumyajit Bagchi | 2025-03-10 | #PDF Loader library failing to read large healthcare PDFs | Sprint 1 | Self | Logical | Replaced PDF Loader with pdfplumber for better parsing | 2025-02-27 | Closed | pdfplumber handled multi-column, complex PDFs
2 | Soumyajit Bagchi | 2025-03-10 | Groq API Key invalid error during Langchain setup | Sprint 3 | Mentor | API Configuration Issue | Re-generated Groq API key and reconfigured Langchain connection | 2025-03-02 | Closed | API connected successfully after regeneration
3 | Soumyajit Bagchi | 2025-03-10 | Langchain giving hallucinated responses | Sprint 3 | Self | Logical | Issue.mproved chunk overlap and context for better responses | 2025-03-07 | Closed | Adjustment & Controlled hallucination with context design

## Sheet2
Logical
User Interface
Maintainability
Standards
Others